## Sheet1
Swim Lessons
Task | Description | Issues | Staff Interested (As many as you want)
Swim Lesson Lesson Plans | Create or adapt red cross lesson plans to create a few lesson plans for each level, or create a generic lesson plan that can be plug and play for various skills/practices | * needs to be completed before planning trainings | Audrey, rachel, Chelsey
Tools and Toys | Create a list of tools and toys to add to create new swim lesson crates/stations to increase our abilities and quality of classes, including task cards, songs list, lesson plan packets, testing guides, skills progression guides. Also possibly rename/rebrand the locations instead of numbers |  | Chelsey
Swim lesson trainings | create both initial as well as ongoing in-service trainings for each swim lesson level, aquatots, preschool 1-3, youth 1-5, comp, adults, adaptive, communicating with parents, teaching techniques, professional attitude, stroke training, instruction quality, this includes slide shows, but also videos of each skill, teaching pattern, and class management | *videos would have to be filmed before or after the closure, inservices should include stroke training/teachbacks | Chelsey
Activity List | Compile a list of activities for every skill from aquatots through comp, break down each activity to explain how it works on the skills, as well as what levels it is applicable for(all activities must properly practice a skill, be safe, and be child and workplace appropriate) |  | rachel, Chelsey
Songs list | compile a list of songs, their lyrics, and what activities they can be used for(must be workplace and child appropriate) |  | Chelsey
swim lesson location map | create a blank map of the center(using the rotation map) to create a laminated poster for the white board to use for marking the various swim lesson stations with magnets(so that we can move them when pools close) |  | Crocker
swim lesson faq pamplet | create a trifold of important swim lesson information like, make up policy, lesson locations are not linked to levels, parental pressence required, communication with senior lifeguard etc |  | Audrey, Cisneroz
report cards | potential redesign of report cards, potentially even moving to a single card per level that the parent/student could bring with them to the start of a session so that we can take down what they have already completed to update our whiteboards and eliminate the need to hand out report cards every session(just update the one they have and then sign off on it once they have completed the exit assessment. Put initials and possibly dates next to each skill for check off | *find a way to make red cross materials work | Audrey, Crocker, Chelsey
red cross lesson records | training for WSI certified seniors on how to enter/track our swim lesson records with the red cross |  | Chelsey
Assign lead(s) for swim lesson training
Separate in-service training tracks for lifeguards and swim instructors in-services, then bring everyone together for team activities at the end |  | how will LG and AI staff choose their track? AI track for non LG only?
Lesson evaluation standards | red cross standards |  | Chelsey
swim lesson welcome packet/materials | create a packet with need to know info about our program/levels also have staff do introductions/orientation on the first day of classes. possibly send out as an email |  | John
Lifeguards
Task | Description | Issues | Staff Interested
LG locations | create a slideshow that shows a picture of each guard location, the view of the zone from that guard location, what the zone is for that location, the responsibilities and things to look out for on that location, zone vs total vs emergency coverage for that location | *pictures will need to be done before or after the closure, videos of scanning/walking behavior | Hector, Isaac
LG rotation map | create a new rotation map that potentially rebrands the lifeguard locations to reflect which pool they are on instead of a color, possible create one long rotation that will snake throughout the entire pool deck but also include DT throughout the rotation so that instead of guards only working one rotation, they would end up working all rotations in a shift. | one long rotation wont work with dispatchers, 15 yr olds, or those without slide/river operator training | Crocker, Hector
Pool Tech/Senior Lifeguard
Task | Description | Issues | Staff Interested
pool tech trainings | film and create slideshows and videos for all pool tech tasks, to be used in new sr/pt trainings as well as an ongoing resource to reference when doing tasks | *any tasks on the pool deck would have to film videos before or after the closure | Hector
pool tech/sr tasks | create a new daily task list for cleaning task/maintenance tasks to be completed by the sr/pt/lg on shift throughout that day, this will be done to ensure that we start completing the monthly maintenance checklist instead of putting it all on the PT |  | Hector
meet the seniors | add into newark guard a page dedicated to meeting the senior lifeguard team(possibly also full time staff) with a picture and short bio of each senior | *need headshots | Branden
senior lifeguard orientaion | revamp the senior lifeguard orientation slideshow to include the new manual and training outline |  | John
Senior Lifeguard Specialties | This would be a potential pilot program to create specific roles or specialties for each senior, a dedicated part of our programs that would be the responsibility of that senior to coordinate/train/track |  | rachel, John, Branden
Emergency equipment checks |  |  | hector
Chemical safety procedures |  |  | hector
Cleaning probes and calibration |  |  | hector
PPE review and proper usage |  |  | hector
Equipment inspection checklists |  |  | hector
Basic troubleshooting guide for common pool issues |  |  | hector
Operations
Task | Description | Issues | Staff Interested
In-service modules | create a list of skill/activities (both lg and AI) so that we can create a pick and choose assortment for creating different inservices(ie multiple different activities for active victim practice, multiple types of warm ups/quiz/swim, multiple mock rec scenarios, multiple team building exercises). Each in-service potentially to cover a swim activity, AI training, LG trainings, and Mock Rec all in on day. |  | Sophia, Cisneroz
operations | compile a list of potential improvements to our operations
Digi training videos | screen record new training videos for digi where each video will either talk about a specific function(clock in and out/timesheet, sub request, vacation requests) or will talk about entire modules(maintenace, chemical, employee) |  | Cisneroz
newark guard slideshow | revamp the new orientation slideshow to include elements created above |  | Branden
newark guard welcome test | redo the welcome test to be a quiz of their knowledge |  | Branden
onboarding/training checklists | create a list for each position (AI, LG, PT, SR) for the items they need to be trained on, each item should be signed off by staff and their trainer along with a date. Create a staff training binder so that we can keep track of who needs which training |  | John
employee manuals | critique the current employee position manuals for AI, LG, PT, and SR. Make additions, subtractions and changes as neccesary to cover all aspects of each role
staff certifications needed | go through the certification module and export the list, break it down into each certification so we can see who needs what certs(lg, waterpark, oxygen, T22, slide dispatch) and then work to coordinate a training for each training(most pressing to be schedule first) | *create a yearly trainings schedule to cover the certifications at a regular interval | Branden
slide operator video | potentially refilm the entire slide operator and slide inspector videos | * video would have to be filmed before or after the closure
coaching and counseling | brainstorm ways to implement the senior lifeguards taking a more active role in the coaching process, Ryan is not able to keep up with meeting with staff that are not here regularly, so we need to come up with solutions to get coachings done in a timely and complete manor |  | Branden, Isaac
summer/year round mentee teams | create new mentor/mentee teams like last summer, dual captains for each team, potential year round points, atleast year round coaching and audits |  | Branden, Cisneroz
audit tracker | create a tracker for conducting audits, LG and AI from red ball, brick, live recognition, swim instructor, so that we can make sure that all staff are getting audited at least once(probably more) per season | not to include whether staff pass/fail but rather as ongoing live action practice of their skills | Sophia, Isaac
Run Title 22 trainings,recertifications, and lifeguard class planning | Organize and teach title 22 classes to current LG staff, plan future certification classes for LG, T22, Waterpark, Oxygen |  | Branden
Skills verification standards and documentation | regularly scheduled yearly trainings |  | John
Review and update opening and closing procedures |  |  | John
AFR and ADA checklists
DigiQuatics review | Check for missing forms (chem logs, operations checklists, etc.) Improve consistency in logging |  | John
Supplies and inventory review |  |  | Isaac
Plan in-service week schedule |  |  | Branden, Cisneroz
Review and improve swim test procedures
Emergency action plan review and updates
Standardize daily operational checklists
Recruitment, send them to job fairs etc… |  |  | Branden
Jr guard and Jr instructor camp | create schedule and curriculum for week long camp for junior lifeguards and junior instructors(aides) for 12-15yr
Find a clear radio channel
customer service training for Sr LG and LG | videos for staff to watch or trainings on de-escalation and general customer service situations and verbiage
Team Morale / Culture
Plan and organize summer team structures |  |  | Cisneroz
Create team-based competitions or point systems |  |  | Cisneroz
Develop recognition ideas for guards and instructors |  | We have a committee set up which consists of seniors and regular staff to plan Beach Day and Awards Night. Do we expand it for summer outings as well? | Branden
Plan morale events during the season |  |  | Branden
End-of-season awards or incentives |  |  | Branden
Each team could produce:
Written procedures
Checklists
Training documents
Short training videos
Updated forms or materials